## Read Me
MoSJE Portal — Design QC Tracker
Status tracker for design-fidelity defects (dev-facing). Visual evidence lives in the annotated PDF report; design-improvement ideas live in the separate Design Suggestions doc.
HOW TO USE
1. | Each fidelity defect = one row in its portal's findings sheet. The annotated PDF shows the same ID on the image.
2. | Severity / Category / Status are dropdowns; Severity auto-colours; Rollup aggregates automatically.
3. | Figma URL and Live URL are full clickable links. Coverage tracks every screen's QC state.
4. | Dev: filter Status = Open, fix, set Fixed. QC verifies -> Verified.
5. | Design-side issues (design-bugs, redesigns, no-design screens) are NOT here — see Design Suggestions doc.
SEVERITY | Impact, not effort
Blocker | Breaks experience / brand / compliance. Cannot ship.
Major | Clearly wrong vs design; users notice.
Minor | Visible to a trained eye (2-7px, token drift).
Nit | Polish / sub-pixel.
CATEGORIES | Layout & Spacing · Color & Token · Typography · Components & States · Content & Iconography · Responsive & A11y
DESIGN TRUTH | Audited against DS Figma token values (see design-truth-tokens.md). DS brand primary = #003366.

## Rollup
Portal QC — Rollup
Portal | Total | Blocker | Major | Minor | Nit | Open | Fixed | Verified
eUtthan Admin

## eUtthan Admin
ID | Screen | Viewport | Category | Severity | Issue (Design → Built) | Recommended Fix (Dev) | Figma URL | Live URL | Status | Assignee | Date | Notes
UTH-GLOBAL-001 | Global — Common Elements | 1440 | Layout & Spacing | Minor | Figma: Height 40px, navy #003366 background. → Live: Height 38px (colour is correct). | Increase the accessibility bar height from 38px to 40px. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-002 | Global — Common Elements | 1440 | Content & Iconography | Major | Figma: Two lines: 'Ministry of SJE' (14px/500/#1f2937) above the bold 'Department of SJE' headline (20px/700/#374151). → Live: Single line 'Ministry of SJE' at 20px/700/#374151 — the Department headline is absent. | Add 'Department of Social Justice & Empowerment' (20px/700/#374151) as the main masthead headline; show the Ministry line above it at 14px/500/#1f2937. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-003 | Global — Common Elements | 1440 | Content & Iconography | Major | Figma: Centre-right of the masthead: Digital India logo + SAMAVESH lockup, with a 24px gap between them. → Live: No co-branding — the centre of the header is empty. | Add the Digital India logo and the SAMAVESH lockup to the header centre, before the user profile. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-004 | Global — Common Elements | 1440 | Components & States | Minor | Figma: A hamburger/collapse control sits at the top-left of the header. → Live: No collapse control is shown in the header. | Add the sidebar collapse (hamburger) control at the header's left edge. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-005 | Global — Common Elements | 1440 | Color & Token | Major | Figma: Active item: text #003366 · weight 400 · corner radius 16px · background #e5eff9. → Live: Active item: text #374151 · weight 700 · radius 8px (background correct; three properties deviate). | Active sidebar item: text colour → #003366 · weight → 400 · corner radius → 16px. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-006 | Global — Common Elements | 1440 | Content & Iconography | Minor | Figma: Name with the role below it as plain text ('Admin', no punctuation); the avatar sits AFTER the text, at the far right. → Live: Avatar comes first, then the name; the role is wrapped in parentheses — '(Super Admin)'. | Put the name and role first with the avatar to their right, and show the role as plain text without parentheses. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-007 | Global — Common Elements | 1440 | Typography | Major | Figma: All inputs and search fields use Noto Sans, like the rest of the portal. → Live: Search and text inputs render in Poppins on Login and across the Admin and Ministry screens. | Set every input, select and search field to Noto Sans. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-008 | Global — Common Elements | 1440 | Components & States | Minor | Figma: Plus icon to the LEFT of the label; label 14px / 500 / line-height 20; padding 24-left / 16-right / 8 top & bottom; the plus is a separate 16×16 icon. → Live: Plus icon to the RIGHT; label 14px / 600 with a tight line-height; padding 18 / 12 / 0; the '+' is baked into the label text. | On every Add button: plus icon on the left, label weight 500 / line-height 20, padding 24/16/8, and a real plus-icon element. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-009 | Global — Common Elements | 1440 | Typography | Major | Figma: 14px / 600 / colour #6b7280; cell padding 24px on the sides · 16px top & bottom; header sits on a #f9fafb band. → Live: Header text renders in #4b5563 with only 14px top/bottom padding (colour and vertical padding deviate; font-size 14px is correct). | On every table header: text colour → #6b7280; cell padding 24px sides · 16px top/bottom. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-010 | Global — Common Elements | 1440 | Color & Token | Major | Figma: 14px / 400 / colour #374151; cell padding 24px on the sides · 16px top & bottom. → Live: Body cells render with a different colour (#4b5563, or pure #000 on some screens) and less top/bottom padding (16–20px). | On every table body cell: text colour → #374151; cell padding 24px sides · 16px top/bottom. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-GLOBAL-011 | Global — Common Elements | 1440 | Color & Token | Minor | Figma: The search bar and table sit directly on the page with a soft shadow — there is NO bordered card around them. → Live: The search and table are wrapped in a 1px hairline-bordered card. | Remove the hairline card border around the search + table; use the soft shadow from the design. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 |  | Open
UTH-LOGIN-001 | Login | 1440 | Components & States | Blocker | Figma: Navy government bar at the very top — flag + 'Government of India', 'Skip to Main Content', A−/A/A+ text resize, contrast toggle and language selector. → Live: The login page has no government bar at all (the signed-in pages do have it). | Add the same government accessibility bar to the top of the login page. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=9018-36746 | https://eutthan-admin-uat.mosje.in/login | Open
UTH-LOGIN-002 | Login | 1440 | Content & Iconography | Major | Figma: Emblem + BETA tag + the full three-line lockup ending in the bold 'Department of Social Justice & Empowerment', plus the Digital India and SAMAVESH logos. → Live: Only the emblem with two lines; the BETA tag, Department line and both partner logos are missing. | Show the complete masthead: BETA tag, full department lockup, and the Digital India + SAMAVESH logos. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=9018-36746 | https://eutthan-admin-uat.mosje.in/login | Open
UTH-LOGIN-003 | Login | 1440 | Color & Token | Blocker | Figma: A solid navy #003366 brand panel (~60% of the page): SAMAVESH logo + समावेश wordmark, orange divider, 'Justice. Equality. Dignity.' headline, a short description, and a bottom 'SIGNING INTO E-Utthaan' strip with a Change button. → Live: A pale-blue illustration fills the left side (~44%) — no navy panel, no SAMAVESH branding, no tagline and no 'SIGNING INTO' strip. | Replace the illustration with the navy SAMAVESH brand panel, restore the ~60/40 split and the 'SIGNING INTO E-Utthaan' strip. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=9018-36746 | https://eutthan-admin-uat.mosje.in/login | Open
UTH-LOGIN-004 | Login | 1440 | Content & Iconography | Major | Figma: 'Log in to your account' — left-aligned at the top of the form. → Live: 'Log In' — centred, with the national emblem repeated above it. | Use the heading 'Log in to your account', left-aligned, and remove the duplicate emblem above the form. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=9018-36746 | https://eutthan-admin-uat.mosje.in/login | Open
UTH-LOGIN-005 | Login | 1440 | Components & States | Major | Figma: 'User ID or Email' and 'Password' labels sit above their fields; inputs are 48px tall with a navy #003366 focus outline. → Live: No labels — only placeholder text inside the fields; inputs are 46px tall with no visible focus style. | Add the two field labels above the inputs; input height 48px with a 2px navy #003366 focus outline. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=9018-36746 | https://eutthan-admin-uat.mosje.in/login | Open
UTH-LOGIN-006 | Login | 1440 | Components & States | Minor | Figma: Eye icon inside the password field — 24×24, grey #6b7280. → Live: The eye icon is smaller (~16px) and tight against the field edge with a small tap area. | Use the 24px eye icon in grey #6b7280 with a comfortable tap area. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=9018-36746 | https://eutthan-admin-uat.mosje.in/login | Open
UTH-LOGIN-007 | Login | 1440 | Color & Token | Minor | Figma: Label 'Log In' · 48px tall · 8px corner radius · full form width. → Live: Label 'Sign In' · ~41px tall · ~6px radius. | Change the label to 'Log In'; set height 48px and corner radius 8px. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=9018-36746 | https://eutthan-admin-uat.mosje.in/login | Open
UTH-LOGIN-008 | Login | 1440 | Content & Iconography | Nit | Figma: 'Forgot Password?' — with the question mark — right-aligned on the Password label row, in navy. → Live: 'Forgot Password' without the question mark. | Add the question mark: 'Forgot Password?'. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=9018-36746 | https://eutthan-admin-uat.mosje.in/login | Open
UTH-DASHBOARD-001 | Admin / Dashboard | 1440 | Typography | Minor | Figma: Noto Sans 28px / 500 / line-height 36 / letter-spacing −0.28 / colour #374151. → Live: 30px / 600 / colour #1E3A5F (larger, bolder and a different colour). | Set the page heading to 28px / 500 / #374151 / letter-spacing −0.28. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 | https://eutthan-admin-uat.mosje.in/dashboard | Open
UTH-DASHBOARD-002 | Admin / Dashboard | 1440 | Layout & Spacing | Major | Figma: The State and Financial-Year filters sit at the top of the page, next to the 'Dashboard' heading — they control everything below. → Live: The Financial-Year filter sits inside the 'Progress Report' panel header, although changing it also updates the four KPI cards above it. | Move the Financial-Year filter to the top of the page next to the heading, as it affects the whole page. Applies to the Ministry dashboard as well. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 | https://eutthan-admin-uat.mosje.in/dashboard | Open
UTH-DASHBOARD-003 | Admin / Dashboard | 1440 | Components & States | Minor | Figma: Two filters at the top: a State dropdown ('All States') and the Financial-Year dropdown. → Live: Only the Financial-Year filter exists; there is no State filter. | Show all the relevant filters. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 | https://eutthan-admin-uat.mosje.in/dashboard | Open
UTH-DASHBOARD-004 | Admin / Dashboard | 1440 | Typography | Major | Figma: Card label in regular weight (400) dark slate #374151; the value below in semibold dark slate #374151. → Live: Card labels render in bold, and all values render in bold navy (#003366 family) — heavier and bluer than the design. | Card labels → regular 400 #374151; values → semibold #374151 (not navy, not extra bold). Applies to both dashboards. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 | https://eutthan-admin-uat.mosje.in/dashboard | Open
UTH-DASHBOARD-005 | Admin / Dashboard | 1440 | Layout & Spacing | Minor | Figma: 'Progress Report of Financial Year …' is a plain section title on the page, with the white stat cards directly below it. → Live: The whole progress section is wrapped in a grey panel with a header strip, so the cards sit inside a box that isn't in the design. | Remove the grey wrapper panel; show the section title directly on the page with the cards below. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 | https://eutthan-admin-uat.mosje.in/dashboard | Open
UTH-FINANCIAL-YEAR-001 | Admin / Financial Year | 1440 | Color & Token | Major | Figma: Financial-year body cells use navy #003366 (this screen highlights the value in primary). → Live: Body cells render in #374151 — the navy treatment is missing. | Set the body cell text to navy #003366 on this screen. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40009 | https://eutthan-admin-uat.mosje.in/admin/financial-year-management | Open
UTH-FINANCIAL-YEAR-002 | Admin / Financial Year | 1440 | Components & States | Major | Figma: The right-most column has an 'Action' header above the row controls. → Live: No 'Action' header above the edit/delete controls. | Add the 'Action' column header to the table header row. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40009 | https://eutthan-admin-uat.mosje.in/admin/financial-year-management | Open
UTH-FINANCIAL-YEAR-003 | Admin / Financial Year | 1440 | Components & States | Major | Figma: Two icon-only buttons per row: a pencil (edit) in a light box and a red trash (delete) in a light-red box. → Live: An 'Edit' text link with a pencil, plus a bare trash icon — not the boxed icon-only buttons. | Use the boxed icon-only pencil and red trash buttons from the design. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40009 | https://eutthan-admin-uat.mosje.in/admin/financial-year-management | Open
UTH-FINANCIAL-YEAR-004 | Admin / Financial Year | 1440 | Color & Token | Minor | Figma: Highlighted/selected row background #e5eff9. → Live: Highlighted row background #eaf2fb — visually close but not the token. | Use #e5eff9 for the highlighted row background. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40009 | https://eutthan-admin-uat.mosje.in/admin/financial-year-management | Open
UTH-FINANCIAL-YEAR-005 | Admin / Financial Year | 1440 | Color & Token | Minor | Figma: Search field has a white background (border #e5e7eb). → Live: Search field background is grey #f9fafb (border #e5e7eb is the same in both). | Set the search field background to white. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40009 | https://eutthan-admin-uat.mosje.in/admin/financial-year-management | Open
UTH-MANAGE-MINISTRY-001 | Admin / Manage Ministry | 1440 | Color & Token | Major | Figma: Default rows in neutral dark #374151; a row turns primary navy #003366 (on the #e5eff9 highlight) only on hover/selection. → Live: Ministry names always render in a lighter blue link style, regardless of state. | Default rows → #374151; apply the navy #003366 treatment only to the hovered/selected row. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40288 | https://eutthan-admin-uat.mosje.in/ministry-management | Open
UTH-MANAGE-MINISTRY-002 | Admin / Manage Ministry | 1440 | Components & States | Major | Figma: On the hovered row: 'Edit' (navy on a light fill, 8px radius) and 'Delete' (red text + icon), comfortably sized with a 12px gap. → Live: Edit and Delete appear but are compressed by the tight row padding and can't render at their designed size. | Match the Edit/Delete buttons' size, fill and spacing to the design. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40288 | https://eutthan-admin-uat.mosje.in/ministry-management | Open
UTH-MANAGE-OUTCOME-001 | Admin / Manage Outcome | 1440 | Components & States | Minor | Figma: Three filter chips beside the search: Financial Year, 'All Schemes' and 'All Department'. → Live: Only the Financial-Year dropdown is present. | Show all the relevant filters. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40657 | https://eutthan-admin-uat.mosje.in/manage-outcome | Open
UTH-DOCUMENTS-001 | Admin / Documents | 1440 | Components & States | Major | Figma: A compact filter chip (about 99×36, 6px radius, 1px #e5e7eb border, leading arrow-down icon). → Live: A wide clearable select with a trailing × button and chevron — a different control style. | Use the compact filter-chip style from the design; keep the × clear only for an applied-filter state. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-42902 | https://eutthan-admin-uat.mosje.in/document-management | Open
UTH-MAP-MINISTRY-001 | Admin / Map Ministry / Mapped | 1440 | Components & States | Blocker | Figma: A two-option segmented control sits beside the heading — active 'Ministry' in white on navy #003366, inactive 'Schemes' in grey. → Live: No tabs at all — the 'Mapped Ministry List' heading sits alone above the table. | Add the Ministry/Schemes segmented tabs beside the heading, as shown in the design. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-41073 | https://eutthan-admin-uat.mosje.in/map-ministry | Open
UTH-MAP-MINISTRY-002 | Admin / Map Ministry / Mapped | 1440 | Color & Token | Major | Figma: Body cells use neutral dark #374151. → Live: Ministry-name cells render in navy #003366 with a link treatment that isn't in the design. | Set the body cells to #374151; remove the navy link treatment. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-41073 | https://eutthan-admin-uat.mosje.in/map-ministry | Open
UTH-MAP-MINISTRY-003 | Admin / Map Ministry / Mapped | 1440 | Color & Token | Major | Figma: 'Unmap' is a quiet text button in navy #003366 (text + icon). → Live: 'Unmap' renders in red (~#ef4444) — a danger treatment the design doesn't use. | Recolour the Unmap text and icon to navy #003366. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-41073 | https://eutthan-admin-uat.mosje.in/map-ministry | Open
UTH-MANAGE-USER-001 | Admin / Manage User | 1440 | Components & States | Minor | Figma: Three filter dropdowns beside the search field. → Live: A single 'All Years' select only. | Show all the relevant filters. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40865 | https://eutthan-admin-uat.mosje.in/user-management | Open
UTH-MIN-DASHBOARD-001 | Ministry / Dashboard | 1440 | Components & States | Minor | Figma: The filter control uses an 8px corner radius and sits at the top of the page. → Live: The Financial-Year selector uses a 6px radius and sits inside the progress panel header (placement covered under Admin · Dashboard). | Set the filter control radius to 8px. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-37114 | https://eutthan-admin-uat.mosje.in/dashboard | Open
UTH-MIN-DASHBOARD-002 | Ministry / Dashboard | 1440 | Typography | Major | Figma: Card label regular 400 #374151; value semibold #374151. → Live: Labels bold, values bold navy — same deviation as the Admin dashboard. | Card labels → regular 400 #374151; values → semibold #374151. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-37114 | https://eutthan-admin-uat.mosje.in/dashboard | Open
UTH-MIN-SCHEME-MANAGEMENT-001 | Ministry / Manage Scheme | 1440 | Components & States | Minor | Figma: An 'All Department' dropdown sits beside the Financial-Year filter. → Live: Only the Financial-Year filter is present. | Show all the relevant filters. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-37360 | https://eutthan-admin-uat.mosje.in/scheme-management | Open
UTH-MIN-MANAGE-OUTCOME-001 | Ministry / Manage Outcome | 1440 | Components & States | Minor | Figma: 'All Schemes' and 'All Department' dropdowns sit beside the Financial-Year filter. → Live: Only the Financial-Year dropdown is present. | Show all the relevant filters. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-38577 | https://eutthan-admin-uat.mosje.in/manage-outcome | Open
UTH-MIN-MINISTRY-PHYSICAL-PROGRESS-DATA-001 | Ministry / Physical Progress Data | 1440 | Components & States | Minor | Figma: Two actions: 'Import Achievements Data' (outline) and 'Add Progress' (filled navy). → Live: A third button — 'Download Sample Template' — appears to the left of Import. | Confirm whether the extra 'Download Sample Template' action is intended; the design shows two actions. | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-38368 | https://eutthan-admin-uat.mosje.in/ministry/physical-progress-data | Open

## Coverage – eUtthan
Screen | Section | Figma URL | Has Design? | Built? | QC Status | # Findings | Notes
Ministry / Dashboard | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-37114 | Yes | Yes | Done
Ministry / Manage Scheme | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-37360 | Yes | Yes | Done
Ministry / Manage Scheme (scrolled) | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-37568 | Yes |  | Not Started
Ministry / Add | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-38254 | Yes |  | Not Started
Ministry / Physical Progress Data | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-38368 | Yes | Yes | Done
Ministry / Manage Scheme (scrolled) | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-37796 | Yes |  | Not Started
Ministry / Manage Scheme (scrolled) | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-38041 | Yes |  | Not Started
Ministry / Physical Progress Data / Add | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39568 | Yes |  | Not Started
Ministry / Physical Progress Data / Import Excel | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39128 | Yes |  | Not Started
Ministry / Physical Progress Data / Import Excel (uploaded) | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39348 | Yes |  | Not Started
Ministry / Manage Outcome | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-38577 | Yes | Yes | Done
Ministry / Manage Outcome | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-38785 | Yes | Yes | Done
Ministry / Manage Outcome / Add | Ministry | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39013 | Yes |  | Not Started
Admin / Dashboard | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-39685 | Yes | Yes | Done
Admin / Financial Year | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40009 | Yes | Yes | Done
Admin / Financial Year / Add | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-43777 | Yes |  | Not Started
Admin / Financial Year | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40148 | Yes | Yes | Done
Admin / Financial Year / Edit | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-44550 | Yes |  | Not Started
Admin / Manage Ministry | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40288 | Yes | Yes | Done
Admin / Manage Ministry / Add | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-43881 | Yes |  | Not Started
Admin / Manage Scheme | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40449 | Yes | Yes | Done
Admin / Manage Scheme (scrolled) | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-43077 | Yes |  | Not Started
Admin / Manage Scheme / Add | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-43990 | Yes |  | Not Started
Admin / Manage Outcome | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40657 | Yes | Yes | Done
Admin / Manage Outcome (scrolled) | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-43305 | Yes |  | Not Started
Admin / Manage Outcome / Add | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-44105 | Yes |  | Not Started
Admin / Documents | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-42902 | Yes | Yes | Done
Admin / Documents / Add | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-44221 | Yes |  | Not Started
Admin / Documents / Add | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-44329 | Yes |  | Not Started
Admin / Map Ministry / Mapped | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-41073 | Yes | Yes | Done
Admin / Map Ministry / Unmapped | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-41283 | Yes |  | Not Started
Admin / Map Schemes / Map | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-42430 | Yes |  | Not Started
Admin / Map Schemes / Mapped | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-41490 | Yes |  | Not Started
Admin / Map Schemes / Mapped | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-41730 | Yes |  | Not Started
Admin / Map Schemes / Map | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-42650 | Yes |  | Not Started
Admin / Map Schemes / Mapped | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-41970 | Yes |  | Not Started
Admin / Map Schemes / Unmap | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-42210 | Yes |  | Not Started
Admin / Manage User | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-40865 | Yes | Yes | Done
Admin / Manage User | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-43533 | Yes | Yes | Done
Admin / Manage User / Add User | Admin | https://www.figma.com/design/gH2vQ62cfg4677YKWuOpLc/MoSJE-Portal--Handoff-?node-id=4226-44437 | Yes |  | Not Started
Login | Admin | — (no design) | No | Yes | Done
Role Management | Admin | — (no design) | No |  | Not Started
PFMS Logs | Admin | — (no design) | No |  | Not Started
Reports / Financial Summary | Admin | — (no design) | No |  | Not Started
Reports / Statement 10A | Admin | — (no design) | No |  | Not Started