## Summary
Design and build sync
Akash Kumar, Designer ¦ Runs in the same pass as the UX4G move
Stage 1 - what we found
Modules recorded
Design-team led
BA led
Mixed
Still unknown
Captured (stage 2)
Stage 3 - triage mix
Screens triaged
Tier 1 - UX4G only | Expect most screens here.
Tier 2 - targeted fix
Tier 3 - full redesign | The expensive tier. Watch this share.
Tier 3 share | If this climbs well above a quarter, scope has grown. Raise it early.
Redesign complete
Follow-on work created
Needs stakeholder sign-off again | Tier 3 screens, by our proposed rule.
Build work flagged to dev | Flag when the tier is set, not when the design is done.
How to use this
- Blue on yellow means fill it in. The grey italic row under each header is an example - overwrite it.
- Stage 1: fill the Module Register. Classify each module, then note what the BAs left behind.
- Stage 2: capture the built screens, tick Captured, then list each screen on the Screen Triage sheet.
- Stage 3: give every screen a tier and a written reason. The reason is what you show when asked why a module took the time it did.
- Sequence modules to match the UX4G portal order so no portal gets opened twice.

## Module Register
Module register (stage 1)
Every module, and whether the design team was involved. Classify by: our Figma frame exists, a handoff doc exists, or ask whoever built it.
Portal | Module | Origin | What the BAs left behind | Where it is | Captured | Sequenced with | Notes
NMBA | Mass pledge reporting | BA led | HTML prototype, AI-assisted | link or path | No | Week 7 with NMBA | No Figma source exists
Row 6 is an example - overwrite it. Where nothing survives, the running application is the record and stage 2 covers it.

## Screen Triage
Screen triage (stage 3)
One row per screen or state. The tier decides how much work it gets, and the reason is the record of why.
Portal | Module | Screen or state | Tier | Reason for the tier | Sign-off again | Dev work flagged | Status | Notes
NMBA | Mass pledge reporting | Submission form - validation errors | T2 - targeted fix | Errors appear only at the top, so the user cannot see which field failed | No | Yes | Not started
Judge each screen on: can the user finish the task, is the important thing prominent, does it meet our accessibility standard, does it behave like the rest of the estate, does UX4G already have a pattern for it.
Include interactive states, not just pages. Validation, empty, loading, error, modals and multi-step flows are what BA-led modules most often leave undefined.

## Weekly
Weekly figures
Kept separate so neither number hides the other.
Week | Ending | On UX4G | BA work brought up to standard | Tier 3 share | Notes
1 | 08 Aug
2 | 15 Aug
3 | 22 Aug
4 | 29 Aug
5 | 05 Sep
6 | 12 Sep
7 | 19 Sep
8 | 26 Sep
9 | 03 Oct
10 | 10 Oct
11 | 17 Oct
12 | 24 Oct
13 | 31 Oct
If the tier 3 share climbs well above a quarter, the scope has grown beyond what was planned. Better raised in week 4 than in October.