## Summary
UX4G adoption
MoSJE / DoSJE ¦ Akash Kumar, Designer ¦ Upgrading from UX4G 2.0 to 3.0
Dates
First weekly report | 08 Aug 2026
Reporting format needed | 07 Aug 2026 | So the first report is filed in the expected shape.
Clause 2 point raised by | 16 Aug 2026 | Fifteen days from issue.
Replies helpful by | 18 Aug 2026 | After this, open items move to the register and we proceed.
Full transition | 31 Oct 2026
Progress
Figma screens using the library |  | NOT YET MEASURED. This affects the timeline most.
Latest reported (design)
Latest reported (build)
Weeks reported
Questions answered
High-priority questions open
Register entries
Milestones complete
How to use this
- Blue text on yellow means fill it in. Everything else works itself out.
- Questions: twelve items we have asked about. Log replies as they arrive.
- Register: what we decided and why. Anything still open on 18 August moves here and we carry on.
- The register is what lets us answer later questions with a written reason rather than a recollection.

## Portals
Portals
Order of work, and progress against each.
Portal | Order | Already using shared components | Figma screens using the library | Design progress | Planned | Status
NMBA | 1 | Most |  |  | Week 7 | Not started
DoSJE website | 2 | Some |  |  | Weeks 8-9 | Not started
SMILE Admin | 3 | Little |  |  | Weeks 9-10 | Not started
NHAPOA | 4 | Little |  |  | Week 10 | Not started
SCW | 5 | Little |  |  | Week 11 | Not started
Eutthan Admin | 6 | None yet |  |  | Week 11 | Not started
TG | 7 | Some |  |  | Week 11 | Not started
PM-AJAY | 8 | Little |  |  | Week 11 | Not started
OVERALL
Column D is the week 1 measurement. Screens built from library components pick up the upgrade almost automatically; detached ones need reworking individually.
Order of work starts with the portal that already uses shared components most, so the method is proven before it is applied widely.

## Weekly Log
Weekly report log
Design and build reported separately. They will not move at the same rate.
Wk | From | To | Focus | NMBA | DoSJE website | SMILE Admin | NHAPOA | SCW | Eutthan Admin | TG | PM-AJAY | DESIGN overall | BUILD overall | Filed | Notes
1 | 04 Aug | 08 Aug | Measure library use, send questions, first report | [10 empty] | No
2 | 11 Aug | 15 Aug | Duplicate and publish the library, apply colours | [10 empty] | No
3 | 18 Aug | 22 Aug | Raise the clause 2 point, check contrast | [10 empty] | No
4 | 25 Aug | 29 Aug | Map 2.0 against 3.0 | [10 empty] | No
5 | 01 Sep | 05 Sep | Upgrade the library in place | [10 empty] | No
6 | 08 Sep | 12 Sep | Build what UX4G does not cover | [10 empty] | No
7 | 15 Sep | 19 Sep | First portal, to prove the method | [10 empty] | No
8 | 22 Sep | 26 Sep | CHECKPOINT: is the deadline still reachable? | [10 empty] | No
9 | 29 Sep | 03 Oct | Website | [10 empty] | No
10 | 06 Oct | 10 Oct | Next portals | [10 empty] | No
11 | 13 Oct | 17 Oct | Remaining portals | [10 empty] | No
12 | 20 Oct | 24 Oct | Package the contribution | [10 empty] | No
13 | 27 Oct | 31 Oct | Publish the register, final report | [10 empty] | No
Enter each portal's design progress as a percentage. The DESIGN overall column averages them. BUILD overall is entered directly.
Both figures start modest and rise. The trend is the useful part.

## Questions
Questions we have asked
Twelve items. Full wording in the questionnaire. Anything still open on 18 Aug moves to the Register.
# | Section | Question | Why it matters | If we do not hear back | Priority | Status | Reply | Who replied | Date
Q1 | Moving 2.0 to 3.0 | Is there a mapping or upgrade guide from 2.0 to 3.0? | Figma matches components by name when a library is replaced. If names changed between versions, replacing could unlink components across our files. | Compare the versions ourselves, write the mapping, rebuild only what does not match | High | Open
Q2 | Moving 2.0 to 3.0 | If a newer version arrives mid-way, should we adopt it or finish first? | Adopting mid-way means revisiting completed work. | Finish against 3.0; treat any later upgrade as separate work | High | Open
Q3 | Confirming we did it right | How will adoption be checked? | Several checks are possible and each asks for different work: review by eye, our own declaration, components tracing to the published library, name and structure matching, or an accessibility review. | Report on component and structure matching, method shared weekly | High | Open
Q4 | Confirming we did it right | Who confirms a design is compliant, and at what point? | Gives us a clear definition of finished. | Record every submission; treat no response within two weeks as accepted | High | Open
Q5 | Confirming we did it right | Is there a preferred format for recording a departure from the kit? | We would rather use an existing format than invent one. | Use our own register and share it weekly | Medium | Open
Q6 | Brand alignment | DBIM sets structural colour rules (footer uses the darkest shade of the key colour group; icons use the key colour or white). Do these apply inside UX4G components? | The few places where DBIM and UX4G could point in different directions. | Follow DBIM for footer, icons and identity marks; UX4G elsewhere | High | Open
Q7 | Brand alignment | DBIM defines a type scale and so does UX4G. Which should we follow? | Both specify Noto Sans, so this is only sizes and spacing, but it affects every screen. | UX4G's scale inside components, DBIM's for page-level content | High | Open
Q8 | Components not yet covered | Where 3.0 has no component, should we build on UX4G's foundations or wait? | Dense tables, dashboards, approval chains, maps and monitoring screens sit outside citizen service journeys. | Build on UX4G foundations, record each, offer back | High | Open
Q9 | Components not yet covered | Is anyone already building these, or are they planned for a later release? | If the work exists or is coming, we would rather wait than duplicate it. | Assume none exists yet and build our own | High | Open
Q10 | Components not yet covered | If we build them, how would you like them submitted? | The directive asks us to contribute back and we would like to do it properly. | Package as a Figma file with written specifications | Medium | Open
Q11 | Scope | Does this apply to portals already built and live, or new work only? | Affects the size of the job more than anything else here. | Upgrade existing portals alongside new work, report on both | High | Open
Q12 | Scope | Do already-approved designs need approving again once re-themed? | Some screens are already signed off and re-theming changes how they look. | Re-theme without seeking approval again unless layout or content changes | Medium | Open
When a question closes as 'No reply - assumed', copy it into the Register with its assumption. That is what makes the reasoning easy to explain later.

## Register
Decision register
What we decided and why, recorded for transparency. Shared with each weekly report so nothing arrives as a surprise.
# | Decision | Reasoning | Recorded | Open until | Status | Comments received | Notes
R1 | Duplicate the UX4G Community file, move it to our team project, publish it as one library used across every portal | Follows the published UX4G guidance, and one library keeps all portals consistent. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
R2 | Apply the ministry's key colour group through Theme Craft, leaving component structure, spacing and states untouched | DBIM sets the colour group and Theme Craft is UX4G's own way of applying it. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
R3 | Check the 2.0 to 3.0 component mapping before changing the library, rather than replacing it outright | Component names may have changed between versions, and replacing a library matches by name. Checking first avoids unlinking existing work. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
R4 | Keep our existing Material Symbols icons at the size UX4G specifies | It is the current version of the icon set UX4G uses by default, so the visual language matches. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
R5 | Where UX4G has no component, build on its foundations rather than bringing one in from elsewhere | Keeps everything traceable to UX4G and makes the work useful to others. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
R6 | Only detach a component from the library when we write down the reason | Keeps the file honest and gives us a record if anyone asks later. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
R7 | Treat new page layouts assembled from existing UX4G components as compliant without separate approval | Otherwise every screen needs a sign-off, which would slow things considerably. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
R8 | Continue checking accessibility ourselves at page level | Compliant components do not by themselves make a page accessible. Heading order, focus order and landmarks stay with us. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
R9 | Keep a dated copy of the UX4G kit and guidance as they stood on the day we copied them | So a later question about why something looks a certain way can be answered against the guidance as it was at the time. | 04 Aug 2026 | 18 Aug 2026 | Open for comment
Add a row for every further decision, and for every question that gets no reply. Write the reasoning so it reads well to someone who was not there at the time.

## Milestones
Milestones
Thirteen weeks, 04 August to 31 October 2026.
Wk | Dates | What | Done when | Owner | Status | Notes
1 | 04-08 Aug | Measure how much of our Figma work uses library components | Figure known | Designer | Not started
1 | 04-08 Aug | Send the questions and decisions document | Sent | Designer | Not started
1 | 04-08 Aug | Raise Q1, Q3 and Q8 on the Thursday call | Discussed | Designer | Not started
1 | 04-08 Aug | File the first weekly report | Filed | Designer | Not started
2 | 11-15 Aug | Duplicate the UX4G 3.0 kit and publish it as our library | Published | Designer | Not started
2 | 11-15 Aug | Apply the ministry key colour group through Theme Craft | Applied | Designer | Not started
2 | 11-15 Aug | Check colour contrast across every combination | Verified | Designer | Not started
3 | 18-22 Aug | Raise the clause 2 point | On record | Designer | Not started
4 | 25-29 Aug | Compare our 2.0 components against 3.0 and write the mapping | Mapping written | Designer | Not started
5 | 01-05 Sep | Upgrade the library in place where names allow | Upgraded | Designer | Not started
5 | 01-05 Sep | Rebuild components where the mapping does not hold | Rebuilt | Designer | Not started
5 | 01-05 Sep | Check a sample of every portal for accidental unlinking | Sample checked | Designer | Not started
6 | 08-12 Sep | Build the components UX4G does not cover | Built and recorded | Designer | Not started
7 | 15-19 Sep | First portal, to prove the method | Method proven | Designer | Not started
8 | 22-26 Sep | CHECKPOINT: is the deadline still reachable? | Continue or flag | Designer | Not started
9 | 29 Sep-03 Oct | Website | Done | Designer | Not started
10 | 06-10 Oct | Next portals | Done | Designer | Not started
11 | 13-17 Oct | Remaining portals | Done | Designer | Not started
12 | 20-24 Oct | Package the components we built and submit them | Submitted | Designer | Not started
13 | 27-31 Oct | Publish the decision register and final report | Complete | Designer | Not started
Three external dates: reporting format (07 Aug), clause 2 point (16 Aug), replies to our questions (18 Aug). Week 8 is the internal checkpoint.

## Risks
Risks
Reviewed weekly alongside the report.
# | Risk | Likelihood | Impact | What we do about it | Owner | Status | Notes
K1 | Replacing the library unlinks components across our files, because 2.0 and 3.0 names differ | Medium | Very high | Map the versions first, upgrade in place, test on one portal before going wider. | Designer | Open
K2 | Fewer of our Figma screens use library components than hoped | High | High | Measured in week 1, before we commit to a rate. | Designer | Open
K3 | What counts as compliant is defined late | Medium | High | Report the most objective measure available and keep the register, so any definition can be evidenced afterwards. | Designer | Open
K4 | UX4G has nothing yet for tables, dashboards, charts or maps | High | High | Build on its foundations, record each, offer back. | Designer | Open
K5 | A newer UX4G version lands mid-project | Medium | High | Finish against 3.0 and treat the upgrade as separate work. | Designer | Open
K6 | Structural DBIM colour rules conflict with UX4G component styling | Low | Medium | Asked in the questionnaire; following DBIM for identity in the meantime. | Designer | Open
K7 | Already-approved designs need approving again | Medium | High | Settle it before week 7. | Designer | Open
K8 | The report format differs from what is expected | Medium | High | Ask for the format before 07 August. | Designer | Open
K1 is the one that could undo existing work rather than delay it. Figma matches components by name when a library is replaced, and 2.0 and 3.0 names may differ.